## Sprint Overview
Sprint | Period or week | Objective | Main deliverables | Frontend responsibilities | Backend responsibilities | DevOps and Testing responsibilities | AI/ML responsibilities | Dependencies | Acceptance criteria | Evidence required | Status | Blockers
Sprint 0 | Week 0 (planning estimate) | Validate product direction and boundaries. | Workflow maps; initial architecture, API, security and data-flow inventory. | Map extension/dashboard journeys and accessibility needs. | Document existing routes, identity and session boundaries. | Document prerequisites, environments and quality gates. | Map Ollama/LangGraph/retrieval and evaluation needs. | Developer workflow and source inventory. | Document current evidence and unresolved requirements. | Review notes and architecture walkthrough; no unverified PPT claims. | In Progress | Incubation deck/market analysis artifacts not found.
Sprint 1 | Week 1 (planning estimate) | Stabilize setup and auth/UI contracts. | Local setup, role-aware UI/auth checks, AI config and prompt cases. | Login, navigation, loading/error states. | Audit user roles and core endpoint permissions. | Environment templates and clean setup checks. | Verify current Ollama and guided response behavior. | Supported local toolchain and access to local services. | Auth checks and local startup pass with evidence. | Test logs, setup walkthrough and AI request record. | In Progress | Backend auth is fixed and tested; local service startup not verified.
Sprint 2 | Week 2 (planning estimate) | Align administration, experts and foundational APIs. | Shared components, expert profile/availability and API role tests. | Reusable admin/expert UI, responsive/accessibility states. | Profiles, skills, availability, session APIs and ownership. | API contract, auth isolation and migration tests. | Response metadata for review and knowledge. | Agreed role rules and endpoint contracts. | Participant isolation and role denial verified. | Synthetic expert flow and API test results. | In Progress | Audit-event model and background expiry absent.
Sprint 3 | Week 3 (planning estimate) | Improve AI, retrieval, Visual Expert and learning data. | Grounded prompt evals; authorized source/catalog design. | Evidence-based Skill Quest UI; Visual Expert entry point. | Source/catalog APIs, review and deletion controls. | Ollama, retrieval, ingestion and secret-exclusion checks. | Troubleshooting evals; choose RAG model/index only if supported. | Approved Git source and learning references; model availability. | Cited evidence is authorized; no fabricated course claims. | Evaluation results and synthetic retrieval demo. | In Progress | Visual Expert blocked on authorized Git details; approved course catalogue unavailable.
Sprint 4 | Week 4 (planning estimate) | Integrate extension, dashboard and Human API safely. | Context consent, session lifecycle and approved identity flow. | Advanced scope preview, Human API and dashboard navigation. | Lifecycle, consent, expiry, privacy and shared-auth contracts. | E2E tests for roles, isolation, timeout and reconnect. | Use only consented context; review metadata and escalation. | Context API and identity-provider decision. | No silent expansion or token in URL; ownership tests pass. | Recorded synthetic end-to-end scenarios. | In Progress | One-time application code exchange exists; corporate SSO and realtime notifications remain.
Sprint 5 | Week 5 (planning estimate) | Finish governance, analytics verification and demo. | Accurate metrics, themes, feedback timers and demo-ready states. | Audit/review/knowledge governance and retention. | Regression, clean setup, rollback and release evidence. | Prompt/retrieval/learning evaluation and human correction review. | Verified regression/build/setup results and demo script. | Stable candidate and external service access. | Only evidence-backed features shown; no live-looking sample metrics. | Test/build output, workbook and demo evidence. | In Progress | 114 backend tests pass; npm build/dev and HTTP smoke pass; PostgreSQL connects with zero pending migrations; Ollama qwen3:8b inference and extension VSIX packaging pass; Docker and Extension Host unavailable.

## Task Breakdown
Task ID | Sprint | Team | Task title | Detailed task description | Existing file/module | Planned file/module | API or data dependency | Acceptance criteria | Test evidence | Priority | Estimated effort (estimate) | Status | Notes
AUD-01 | Sprint 0 | All teams | Repository audit | Inventory the current app and classify features with source evidence. | docs/CODEBASE_AUDIT.md | docs/CODEBASE_AUDIT.md | Repository access | Feature state is evidence-based; no runtime claims without runs. | Static source review | High | 2 days | Verified Complete | Audit is source inspection only.
CFG-01 | Sprint 1 | DevOps and Testing Team | Portable environment setup | Validate env templates, ignore rules and Windows/manual/Compose setup. | .env.example; Backend/config/settings.py | README.md; Backend/.env.example | PostgreSQL, Ollama | Clean machine can follow steps; secrets remain local. | Startup checks pending | High | 1–2 days | In Progress | Docker unavailable in this environment.
SEC-01 | Sprint 1–2 | Backend Team | Core API permissions | Replace inappropriate AllowAny defaults and add authentication/object ownership coverage. | Backend/apps/nexus/views.py | Backend/tests/test_api.py | Role policy | Anonymous denied; permitted role and owner access covered. | 114 backend tests pass | Critical | 2–4 days | Verified Complete | Production permission review remains.
UI-01 | Sprint 1–2 | Frontend Team | Shared UI foundations | Refine responsive layout, accessibility, role-aware navigation and states. | Frontend/src/App.jsx; Frontend/src/components/Layout.jsx | Frontend/src/components/ | Backend API contract | Routes present correct empty, error and permission states. | npm run build passed; per-page chunks emitted | Medium | 3–5 days | In Progress | Preserve existing routes.
HUM-01 | Sprint 2–5 | Backend Team | Human API lifecycle | Complete request, accept/decline, active messaging, close/expire, outcome and audit behavior. | Backend/apps/collaboration/ | Backend/apps/collaboration/ | Expert role and retention policy | Server enforces all transitions, consent and participant isolation. | 114 backend tests pass; browser E2E pending | High | 5–8 days | In Progress | No background worker found.
AI-01 | Sprint 3–5 | AI/ML Team | Guided mentor evaluation | Add evaluation cases for context gaps, unsafe requests, retries and escalation. | Backend/ai/orchestrator/; Backend/ai/prompts/ | Backend/tests/evaluation/ | Local Ollama model | Mentor responses use evidence/uncertainty and avoid direct fixes. | Evaluation run pending | High | 5–10 days | In Progress | Do not conflate generator features with mentor mode.
VE-01 | Sprint 3–4 | AI/ML Team | Visual Expert knowledge | Build optional, cited, authorized source retrieval and review workflow. | No current implementation found | Backend/apps/knowledge/ or existing source module | Approved Git URL/repository/access | Source authorization, citations, exclusion and deletion checks pass. | Blocked | High | 5–10 days | Blocked | Do not clone/index until authorization is supplied.
SQ-01 | Sprint 3–5 | Backend Team | Learning catalogue | Add source/review metadata and user usefulness/progress actions. | Backend/apps/collaboration/models.py; Frontend/src/pages/Learning.jsx | Learning catalog model/API | Approved course references | Recommendation rationale/evidence and review date visible. | API/UI tests pending | Medium | 3–6 days | In Progress | Internal links not provided.
EXT-01 | Sprint 4 | Frontend Team | Permission-controlled Advanced Chat | Preview exact files/scope; honor exclusions and support approve/reject/narrow/cancel. | NEXUS Extension/extension.js | NEXUS Extension/extension.js | Workspace selection policy | No read or transmit without consent; paths bounded to workspace. | Node syntax check passes; interactive tests pending | High | 4–6 days | In Progress | Do not read env/key files.
SSO-01 | Sprint 4 | Backend Team | Dashboard session reuse | Implement a one-time application code exchange; corporate IdP is a separate future integration. | Backend/apps/users/; extension/dashboard login | Existing auth modules | Configured dashboard origin and callback allowlist | Short-lived exchange; replay/expiry/origin tests; no JWT URL token. | SSO API tests pass | High | 4–8 days | In Progress | Corporate identity provider not identified.
EXT-02 | Sprint 4 | Frontend Team | Local conversation history | Add bounded thread history, switching, timestamps and clear-history controls while keeping source context out of persisted state. | NEXUS Extension/extension.js | NEXUS Extension/extension.js | VS Code webview state and existing conversation_history API field | Threads switch correctly; raw selected/approved files are not persisted; prior turns are sanitized server-side. | Extension/webview syntax and VSIX packaging pass; Extension Host interaction test pending | High | 2?4 days | In Progress | Visible text/results are local; extension-host code context is session-only.
ANA-01 | Sprint 5 | Frontend Team | Analytics integrity | Remove or label hard-coded fallback values and ensure metrics map to API evidence. | Frontend/src/pages/Dashboard.jsx; Frontend/src/pages/Agents.jsx | Same pages | Analytics metric definitions | Missing data appears unavailable/empty, never invented as live. | No fallback metrics; npm run build passes | High | 2–4 days | In Progress | Fallback metrics removed; npm build and dashboard HTTP smoke pass; browser interaction verification pending.
REL-01 | Sprint 5 | DevOps and Testing Team | Release verification | Run backend tests, frontend build, migration check and clean setup; document outcomes. | Backend/tests; Frontend/package.json | docs/DELIVERY_STATUS.md | Runtime services | Actual commands/results and blockers recorded. | 114 backend tests; Django/migration checks; npm build/dev HTTP smoke; PostgreSQL and Ollama checks; VSIX package passed | High | 3–5 days | In Progress | Browser/Extension Host and external-service checks remain.

## Team Ownership
Team | Ownership boundaries | Primary responsibilities | Interfaces | Cross-team dependencies | Owner (fill in)
Frontend Team | User-facing extension/dashboard behavior; not the authorization source of truth. | React/Vite dashboard, extension webview, navigation, consent UI, themes, accessibility, loading/error/empty states. | Backend APIs, extension messaging, design system. | Backend schemas/permissions; AI context scope; DevOps quality and accessibility criteria.
Backend Team | Server-side policy, persistence, APIs and lifecycle enforcement. | Django models/migrations, auth/permissions, sessions, retention, admin/governance endpoints. | Frontend contracts, AI orchestration, PostgreSQL, identity provider. | Product role policy; DevOps migration/rollback; AI response metadata.
DevOps and Testing Team | Reproducibility and verification; does not own business policy. | Environment setup, CI/build/test scripts, deployment/rollback guidance, regression/security checks. | All runtime components and service owners. | Access to supported toolchains/services; implementation teams provide acceptance criteria.
AI/ML Team | Model behavior, retrieval, source grounding and evaluations. | Ollama/LangGraph/prompts, retrieval, response safety, Visual Expert and Skill Quest evidence logic. | Backend APIs, approved sources, local/authorized model service. | Backend privacy/access boundary; Frontend consent; DevOps evaluation execution.

## Verification and Demo
Sprint | Feature | Expected behavior | Verification steps | Test result | Evidence location | Verified by | Verification date | Remaining issues
Sprint 0 | Architecture audit | Existing stack and limitations cited to source paths. | Inspect manifests, routes, models, client and Git status. | Source inspection recorded; no runtime verification | docs/CODEBASE_AUDIT.md | Codex | 2026-10-19 | No tests/builds performed in audit.
Sprint 1 | Local backend setup | New developer can start Django against PostgreSQL and Ollama. | Follow README in clean supported Windows environment. | PostgreSQL connection and Ollama client inference passed; Django admin HTTP 200 | README.md; docs/DELIVERY_STATUS.md | Codex | 2026-10-19 | pgvector unavailable; Docker and clean-machine setup not checked.
Sprint 2 | Expert isolation | Only developer/assigned expert can access a private session. | Use two developers and two experts; try cross-session read/write. | 114 backend tests passed | Backend/tests/test_collaboration.py | Codex | 2026-10-19 | Browser E2E still pending.
Sprint 3 | ProblemDNA retrieval | Current keyword retrieval returns scoped candidates and does not claim vector search. | Create synthetic records and query similar endpoint. | Backend suite passed; Ollama client inference passed | Backend/ai/retrieval/semantic_search.py; docs/DELIVERY_STATUS.md | Codex | 2026-10-19 | Embeddings disabled.
Sprint 4 | Advanced Chat consent | Files are only read/transmitted after scope approval. | Inspect scope controls; interactive rejection/exclusion testing requires VS Code host. | Syntax passes; interactive verification pending | NEXUS Extension/extension.js | Codex | 2026-10-19 | Workspace Trust/host verification remains.
Sprint 4 | Local extension conversation history | Up to 15 threads can be switched and cleared; source payloads are not persisted by the history feature. | Inspect webview state handling; build/package extension and run Extension Host interaction checks. | Extension/webview syntax and VSIX packaging passed; Extension Host interaction not run | NEXUS Extension/extension.js; NEXUS Extension/README.md | Codex | 2026-10-19 | Code context is session-only.
Sprint 5 | Release regression | Tests/build/migration/setup results accurately recorded. | Run commands in README and record logs/environment. | 114 tests; npm build/dev smoke; PostgreSQL connection and migration plan; local Ollama inference; extension VSIX all pass | docs/DELIVERY_STATUS.md | Codex | 2026-10-19 | Docker and interactive VS Code Extension Host checks remain unavailable.

## Risks and Dependencies
Risk or dependency | Affected sprint | Responsible team | Likelihood | Impact | Mitigation | Required decision or access | Status
Core API authorization needs ongoing coverage as endpoints change. | 1–2 | Backend Team | High | Critical | Require authentication and keep anonymous/owner tests in the suite. | Review permissions for new routes. | Mitigated; continue review
No company Ollama endpoint/auth details are in the repository. | 1, 3–5 | DevOps and Testing Team | Medium | High | Use local Ollama for development and server-side environment placeholders. | Authorized endpoint, network access and credentials. | Blocked
Company Git Visual Expert integration lacks source/repository/access details. | 3–4 | AI/ML Team | High | High | Defer ingestion; build only configuration contract after authorization. | Git host, repository, service account scope, exclusions and deletion rules. | Blocked
Approved internal course catalog is not available. | 3–5 | Backend Team | High | Medium | Keep recommendations generic and label sources; do not invent links. | Reviewed course titles/URLs/catalog access. | Blocked
Embeddings disabled; ProblemDNA uses keyword scoring. | 3–5 | AI/ML Team | Medium | Medium | Document honest current behavior; decide model/dimensions before migration. | Model choice, supported pgvector install and privacy approval. | Open
No company identity provider is configured; current session handoff is application-level only. | 4 | Backend Team | Medium | High | Use callback-bound one-time code exchange for application session reuse. | Company identity-provider/SSO decision. | In progress
Dashboard KPI/agent fallback metrics could be mistaken for live telemetry. | 5 | Frontend Team | High | High | Removed fabricated fallback values and removed inferred time-saved estimates; use only returned telemetry. | Approved analytics definitions and API field semantics. | Mitigated; browser verification pending
Docker executable/runtime unavailable in current environment. | 1, 5 | DevOps and Testing Team | Medium | Medium | Validate manual local setup; run Compose when Docker is available. | Docker Desktop or authorized machine with Docker. | Blocked